## Sheet1
# | action item description | actionee | Due date
1 | Review and issue FE and BE and Correlator CIRM | IET | end June
2 | Transfer CIRM into database | N Whyborn | tbd
3 | draft the ALMA operations principles and distribute to Executives and JAO-CMT | JAO directorate with operations managers | mid June
4 | ESO (and NRAO/JAO) to check/amend procurement rules in order to allow JAO to attend tenders opening, mainly for technical evaluation. | ESO/NRAO/JAO (W Wild, P Jewell, S Igushi) | end June
5 | update the JAO NCR process in order to consider repair validation "MRB", mainly for critical repairs involving liablility of owners | N Whyborn | mid June
6 | coordinate the collection of Executives needs on the CMMS outputs for LRU repair handling | IET | mid June
7 | Update tier definition and iterate with P Jewell | N Whyborn | mid May
8 | send comments to vs6b of the ALMA Maint. Man. Plan to Nick | Operations managers, IET leads, JAO management | end May
9 | contact J Ibsen about incorporating s/w in maintenance man. plan | N Whyborn | end May
10 | replace 'Executives and JAO' by the actual representatives | N Whyborn | end June
11 | organize telecon to prepare for June (29-6 1-7) Ch'ville meeting | N Whyborn | mid June
12 | update Contract management paragraph in vs6b and distribute to all | R Jager | 8th May