## Tier One Test Plan
| Mode Information | [13 empty] | Test Cases
Priority | Mode Name | Number of Spectral Windows per Pol | Bandwidth of Spectral Window (MHz) | Number of channels per Spectral Window per Pol | Spectral Resolution (KHz) | Minimum int time (msec) | Max Data Rate (MB/sec)a | Data rate supported by software (MB/sec) | Max Data rate from 8 spec (GB/sec) | No Antenna Test Date Planned | No Antenna Test Date Actual | Antenna Test Date Planned | Antenna Test Date Actual | Engineering Tests Complete? | Single Beam Position Switching, no antenna motion | Single Beam Frequency Switching, no antenna motion | Single Beam Position Switching, with antenna motion | Single Beam Frequency Switching, with antenna motion | Did Config tool configure the system? | Astrid tabs (Obs Mgmt, Data Display, GBTStatus) correct? | Does GFM Display Data Correctly? | GBTIDL results look ok? | Python Testsing ok? | Test results written up
1 | Mode 1 (H1K/HBW) | 1 | 1250 | 1024 | 1406 | 0.5 | 32 | 32 | 0.3 |  | done |  | done | Yes
2 | Mode 2 (H16K/HBW) | 1 | 1250 | 16384 | 88 | 0.5 | 500 | 32 | 4 | 2013-07-30 | 2013-08-14 | 2013-08-09 | 2013-08-16 | Yes
3 | Mode 3 (H16K/HBW) | 1 | 850 | 16384 | 61 | 0.5 | 500 | 32 | 4 | 2013-07-31 | 2013-08-15 | 2013-08-09 | 2013-08-16 | Yes
4 | Mode 4 (L1/LBW1) | 1 | 187.5 | 32768 | 5.7 | 10 | 50 | 32 | 0.4 | 2013-08-06 | 2013-08-19 | 2013-08-16 | 2013-08-23
| Mode 5 (L1/LBW1) | 1 | 187.5 | 65536 | 2.9 | 20 | 50 | 32 | 0.4
5 | Mode 6 (L1/LBW1) | 1 | 187.5 | 131072 | 1.4 | 30 | 67 | 32 | 0.5 | 2013-08-07 | 2013-08-20 | 2013-08-16 | 2013-08-23
| Mode 7 (L1/LBW1) | 1 | 100 | 32768 | 3.1 | 10 | 50 | 32 | 0.4
| Mode 8 (L1/LBW1) | 1 | 100 | 65536 | 1.5 | 20 | 50 | 32 | 0.4
| Mode 9 (L1/LBW1) | 1 | 100 | 131072 | 0.8 | 30 | 67 | 32 | 0.5
6 | Mode 10 (L8/LBW1) | 1 | 23.44 | 32768 | 0.7 | 5 | 100 | 32 | 0.8 | 2013-08-13 | 2013-08-21 | 2013-08-23 | 2013-08-23
| Mode 11 (L8/LBW1) | 1 | 23.44 | 65536 | 0.4 | 10 | 100 | 32 | 0.8
| Mode 12 (L8/LBW1) | 1 | 23.44 | 131072 | 0.2 | 30 | 67 | 32 | 0.5
| Mode 13 (L8/LBW1) | 1 | 23.44 | 262144 | 0.1 | 40 | 134 | 32 | 1.1
7 | Mode 14 (L8/LBW1) | 1 | 23.44 | 524288 | 0.05 | 75 | 267 | 32 | 2.1 | 2013-08-14 | 2013-08-22 | 2013-08-23 | 2013-08-23
| Mode 15 (L8/LBW1) | 1 | 11.72 | 32768 | 0.4 | 5 | 100 | 32 | 0.8
| Mode 16 (L8/LBW1) | 1 | 11.72 | 65536 | 0.2 | 10 | 100 | 32 | 0.8
| Mode 17 (L8/LBW1) | 1 | 11.72 | 131072 | 0.1 | 30 | 67 | 32 | 0.5
| Mode 18 (L8/LBW1) | 1 | 11.72 | 262144 | 0.05 | 40 | 134 | 32 | 1.1
| Mode 19 (L8/LBW1) | 1 | 11.72 | 524288 | 0.02 | 75 | 267 | 32 | 2.1
8 | Mode 20 (L8/LBW8) | 8 | 23.44 | 4098 | 2.9 | 5 | 100 | 32 | 0.8 | 2013-08-20 | 2013-08-20 | 2013-08-30 | 2013-08-30
| Mode 21 (L8/LBW8) | 8 | 23.44 | 8192 | 1.4 | 10 | 100 | 32 | 0.8
| Mode 22 (L8/LBW8) | 8 | 23.44 | 16384 | 0.7 | 30 | 67 | 32 | 0.5
| Mode 23 (L8/LBW8) | 8 | 23.44 | 32768 | 0.4 | 40 | 134 | 32 | 1.1
9 | Mode 24 (L8/LBW8) | 8 | 23.44 | 65536 | 0.2 | 75 | 267 | 32 | 2.1 | 2013-08-21 | 2013-08-21 |  | 2013-08-30
| Mode 25 (L8/LBW8) | 8 | 11.72 | 4098 | 2.9 | 5 | 100 | 32 | 0.8
| Mode 26 (L8/LBW8) | 8 | 11.72 | 8192 | 1.4 | 10 | 100 | 32 | 0.8
| Mode 27 (L8/LBW8) | 8 | 11.72 | 16384 | 0.7 | 30 | 67 | 32 | 0.5
| Mode 28 (L8/LBW8) | 8 | 11.72 | 32768 | 0.4 | 40 | 134 | 32 | 1.1
| Mode 29 (L8/LBW8) | 8 | 11.72 | 65536 | 0.2 | 75 | 267 | 32 | 2.1
Notes
aMax Data rate is calculated for recording full polarization and all channels at the minimum integration perdio. Each spectral value is represented by 4 bytes.

## Tier Two Test Plan
Mode Information
Priority | Mode Name | Number of Spectral Windows per Pol | Bandwidth of Spectral Window (MHz) | Number of channels per Spectral Window per Pol | Spectral Resolution (KHz) | Minimum int time (msec) | Max Data Rate (MB/sec)a | Data rate supported by software (MB/sec) | Max Data rate from 8 spec (GB/sec) | No Antenna Test Date Planned/ Actual | Antenna Test Date Planned/ Actual | Single Beam Mapping, no frequency switching, with antenna motion | Single Beam Mapping, with frequency switching, with antenna motion | Dual Beam nodding, with antenna motion | Did Config tool configure the system? | Astrid tabs (Obs Mgmt, Data Display, GBTStatus) correct? | Does GFM Display Data Correctly? | GBTIDL results look ok? | Test results written up
1 | Mode 1 (H1K/HBW) | 1 | 1250 | 1024 | 1406 | 0.5 | 32 | 32 | 0.3
2 | Mode 2 (H16K/HBW) | 1 | 1250 | 16384 | 88 | 0.5 | 500 | 32 | 4
3 | Mode 3 (H16K/HBW) | 1 | 850 | 16384 | 61 | 0.5 | 500 | 32 | 4
4 | Mode 4 (L1/LBW1) | 1 | 187.5 | 32768 | 5.7 | 10 | 50 | 32 | 0.4
| Mode 5 (L1/LBW1) | 1 | 187.5 | 65536 | 2.9 | 20 | 50 | 32 | 0.4
| Mode 6 (L1/LBW1) | 1 | 187.5 | 131072 | 1.4 | 30 | 67 | 32 | 0.5
| Mode 7 (L1/LBW1) | 1 | 100 | 32768 | 3.1 | 10 | 50 | 32 | 0.4
| Mode 8 (L1/LBW1) | 1 | 100 | 65536 | 1.5 | 20 | 50 | 32 | 0.4
5 | Mode 9 (L1/LBW1) | 1 | 100 | 131072 | 0.8 | 30 | 67 | 32 | 0.5
6 | Mode 10 (L8/LBW1) | 1 | 23.44 | 32768 | 0.7 | 5 | 100 | 32 | 0.8
| Mode 11 (L8/LBW1) | 1 | 23.44 | 65536 | 0.4 | 10 | 100 | 32 | 0.8
| Mode 12 (L8/LBW1) | 1 | 23.44 | 131072 | 0.2 | 30 | 67 | 32 | 0.5
| Mode 13 (L8/LBW1) | 1 | 23.44 | 262144 | 0.1 | 40 | 134 | 32 | 1.1
| Mode 14 (L8/LBW1) | 1 | 23.44 | 524288 | 0.05 | 75 | 267 | 32 | 2.1
| Mode 15 (L8/LBW1) | 1 | 11.72 | 32768 | 0.4 | 5 | 100 | 32 | 0.8
| Mode 16 (L8/LBW1) | 1 | 11.72 | 65536 | 0.2 | 10 | 100 | 32 | 0.8
| Mode 17 (L8/LBW1) | 1 | 11.72 | 131072 | 0.1 | 30 | 67 | 32 | 0.5
| Mode 18 (L8/LBW1) | 1 | 11.72 | 262144 | 0.05 | 40 | 134 | 32 | 1.1
7 | Mode 19 (L8/LBW1) | 1 | 11.72 | 524288 | 0.02 | 75 | 267 | 32 | 2.1
8 | Mode 20 (L8/LBW8) | 8 | 23.44 | 4098 | 2.9 | 5 | 100 | 32 | 0.8
| Mode 21 (L8/LBW8) | 8 | 23.44 | 8192 | 1.4 | 10 | 100 | 32 | 0.8
| Mode 22 (L8/LBW8) | 8 | 23.44 | 16384 | 0.7 | 30 | 67 | 32 | 0.5
| Mode 23 (L8/LBW8) | 8 | 23.44 | 32768 | 0.4 | 40 | 134 | 32 | 1.1
| Mode 24 (L8/LBW8) | 8 | 23.44 | 65536 | 0.2 | 75 | 267 | 32 | 2.1
| Mode 25 (L8/LBW8) | 8 | 11.72 | 4098 | 2.9 | 5 | 100 | 32 | 0.8
| Mode 26 (L8/LBW8) | 8 | 11.72 | 8192 | 1.4 | 10 | 100 | 32 | 0.8
| Mode 27 (L8/LBW8) | 8 | 11.72 | 16384 | 0.7 | 30 | 67 | 32 | 0.5
| Mode 28 (L8/LBW8) | 8 | 11.72 | 32768 | 0.4 | 40 | 134 | 32 | 1.1
9 | Mode 29 (L8/LBW8) | 8 | 11.72 | 65536 | 0.2 | 75 | 267 | 32 | 2.1
Notes
aMax Data rate is calculated for recording full polarization and all channels at the minimum integration perdio. Each spectral value is represented by 4 bytes.

## Hardware Test Plan
SubSystem | Tests | Module / Mode | Resource | Date Scheduled | Date Completed
Analog | Gain as fn. of freq. | Module 1 | G. Watts
| 1dB compression Point | Module 2 | G. Watts
| Cross-Coupling | Module 3 | G. Watts
| perf. of noise source | Module 4 | G. Watts
|  | Module 5 | G. Watts
|  | Module 6 | G. Watts
|  | Module 7 | G. Watts
|  | Module 8 | G. Watts
ADC | dynamic range | Module 1 | G. Jones
| phase noise | Module 2 | G. Jones
| Cross-Coupling | Module 3 | G. Jones
|  | Module 4 | G. Jones
|  | Module 5 | G. Jones
|  | Module 6 | G. Jones
|  | Module 7 | G. Jones
|  | Module 8 | G. Jones
PFB / Other Filter | dynamic range | H1K/HBW | G. Jones
| Cross-Coupling | H16K/HBW | G. Jones
| filter response function | L1/LBW1 | G. Jones
|  | L8/LBW1 | G. Jones
|  | L8/LBW8 | G. Jones
Time Stamping |  | H1K/HBW | A. Roshi
|  | H16K/HBW | A. Roshi
|  | L1/LBW1 | TBD
|  | L8/LBW1 | TBD
|  | L8/LBW8 | TBD
State Integration |  | H1K/HBW | A. Roshi
|  | H16K/HBW | A. Roshi
|  | L1/LBW1 | TBD
|  | L8/LBW1 | TBD
|  | L8/LBW8 | TBD
Cross-Product Stability | Overnight Test | H1K/HBW | G. Jones / P. Demorest
| Rearm Roach Test | H16K/HBW | G. Jones / P. Demorest
| Reload BOF Test | L1/LBW1 | G. Jones / P. Demorest
|  | L8/LBW1 | G. Jones / P. Demorest
|  | L8/LBW8 | G. Jones / P. Demorest

## Notes and Dependencies
VEGAS Test Plan Matrix
Mark Whitehead / Richard Prestage
| Version 1. | Created 7/29/2013
Notes:
1 | All Hardware and Tier One tests should be completed by Monday 16th September
2 | This spreadsheet accompanies the VEGAS Test Plan Specification Document, currently http://www.gb.nrao.edu/vegas/report/testplan.pdf
3 | All Astronomical tests should configure at least two banks, to ensure multi-bank operation works correctly
4 | Testing of Modes higher than Mode 3 require at least two new HPC modes to be installed (i.e. by 8/6/2013)
5 | Ray must do some manager work before Mode 4 through 29 astronomical testing (i.e. by 8/6/2013)
6 | Melinda must do some config tool work for 8-sub-band modes
7 | Paul and Glenn should be standing by to assist if necessary with each new GPU mode

## Issues
Common to all Modes
1 | CRVAL1 is modified by valon freq and subfreq. Subfreq settings need to be fixed by looking at the need for all modes. (Ray, Melinda, Mark Wagner)
2 | Valon freq setting through roach serial port (Ray)
3 | Normalization of spectra with exposure time. (Ray)
4 | Number of integration in a scan should be equal to that requested by the user. Number of integration in a scan for data from different banks should be same if they are configured in the same way. (Ray and HPC software person)
5 | HPC -- manager start issue; need to reset the coordinator and manager (Ray)
Mode-Specific
1 | None identified at this time