## Labor Estimates Breakout
Item | Machinist(GB) | Machinist(CV) | Tech(GB) | Tech(CV) | Astronomer | Engineer(GB) | Engineer(CV)
Year I | FTE | FTE | FTE | FTE | FTE | FTE | FTE
Compact Feedhorn | 0.2 | [5 empty] | 0.2 | Sri Srikanth
Noise Calibration Module |  | 0.25 |  | 0.25 |  |  | 0.25 | Eric Bryerton
Integrated Downconverter Module |  | 0.1 |  | 0.25 |  |  | 0.25 | Matt Morgan
LO Distribution | 0.1 |  | 0.75 |  |  | 0.25 |  | Steve White (tbd)
M&C biasing, PCB layout & design |  |  | 0.5 |  |  | 0.5 |  | Amy Shelton (tbd)
Mechanical design (overall) | 0.25 |  | 0.25 |  |  | 0.5 |  | Bob Simon
Parallactic Angle Rotator | 0.25 |  | 0.25 |  |  | 0.25 |  | Dennis Egan
Project Management | [5 empty] | 0.125 |  | Steve White
Systems Engineering | [6 empty] | 0.25 | Kamaljet Saini
Project Scientist II |  |  |  |  | 0.5 |  |  | Post Doc
[8 empty] | Labor Costs | 368000
[8 empty] | Parts Costs | 95000
[8 empty] | Travel | 20000
[8 empty] | Contigency | 60000
Year II | [7 empty] | Total | 543000
Noise Calibration Module |  | 0.1 |  | 0.1 |  |  | 0.1 | Eric Bryerton
Integrated Downconverter Module |  |  |  | 0.25 |  |  | 0.25 | Matt Morgan
Project Management | [5 empty] | 0.125 |  | Steve White
Systems Engineering | [6 empty] | 0.25 | Kamaljet Saini
Receiver Assembly and Cabling | 0.25 |  | 0.75 |  |  | 0.5 |  | Bob Simon
Project Scientist II |  |  |  |  | 1 |  |  | Post Doc
Software Development | [5 empty] | 0.5 |  | Amy Shelton (tbd)
[8 empty] | Labor Costs | 295000
[8 empty] | Parts Costs | 95000
[8 empty] | Contigency | 60000
[8 empty] | Total | 450000
Year III
Receiver Engineer | [5 empty] | 0.25 |  | Bob Simon
Project Scientist II |  |  |  |  | 1 |  |  | Post Doc
Software Development | [5 empty] | 0.5 |  | Amy Shelton (tbd)
[8 empty] | Labor Costs GB | 161000
[8 empty] | Parts Costs | 0
[8 empty] | Contigency | 82000
[8 empty] | Total | 243000
[8 empty] | Project Labor Costs | 824000
[8 empty] | Travel | 20000
[8 empty] | Parts Costs | 190000
[8 empty] | Contigency | 182000
[8 empty] | Total | 1216000

## Parts Costs
Parts | Qty | Unit Cost | Extended Cost
Compact Feedhorn | 7 | 2000 | 14000
Phase Shifter and Transistion | 7 | 7000 | 49000
OMT | 7 | 2000 | 14000
Isolators | 14 | 500 | 7000
NCM | 14 | 500 | 7000
LNA | 14 | 3000 | 42000
IDM parts | 7 | 2000 | 14000
LODM&C parts | 1 | 5000 | 5000
Refrigerator | 1 | 8000 | 8000
Parallactic Angle Rotator | 1 | 20000 | 20000
Total |  |  | 180000